## Node Plan
Node | Sub-step | Name | Purpose | Inputs | Outputs | Tools / Tech | Notes
1 |  | Project Input & Setup Interface | Capture all shot metadata + character library before the AI pipeline runs. Static frontend, no server. | User input + character model sheet PNGs | metadata.json + characters.json + named sheet PNGs (browser-downloaded) | HTML + JS + localStorage | Locked: 1a (one big form, +Add shot blocks) + 2a (browser download) + 3a (separate Character Library page). MP4s are NOT uploaded by the form. Each character also carries a poseExtractor field (dwpose default / lineart-fallback for non-humans) for Node 7 routing.
| 1A | Character Library Page (characters.html) | Pre-register every character: upload 8-angle horizontal-strip model sheet + assign display name + choose Node 7 pose extractor (dwpose default / lineart-fallback for non-humans like Jaggu). | User input + sheet PNGs | characters.json + canonically-named sheet PNGs (downloaded) (each character entry carries poseExtractor). | HTML + JS + localStorage | Run once per project before the shot form. Persists to localStorage so the shot form's identity dropdown is populated.
| 1B | Sheet-format quick check | Client-side validation: dimensions, horizontal-strip aspect ratio, alpha-island count ~8. | Uploaded sheet PNG | Pass/fail + warning shown on page | Canvas API | Full alpha-island slicing happens in Node 6; this is early-warning preview only.
| 1C | Shot Metadata Form Page (index.html) | One big form with repeating '+ Add shot' blocks; one block per shot. | User input + character library from localStorage | In-memory shot list | HTML + JS | Prompts user to visit characters.html first if library is empty.
| 1D | Per-shot fields | Capture Shot ID, MP4 filename, character count, per-character (identity dropdown, position L/CL/C/CR/R), duration in frames @25 FPS. | User input | Structured per-shot record | HTML form controls | Identity dropdown sourced from characters.json/localStorage. MP4 file picker captures filename + thumbnail only - no upload.
| 1E | Batch-level fields | Capture project_name, batch_size (RunPod VRAM control), operator notes. | User input | Batch-level config object | HTML form controls | batch_size feeds Node 11D VRAM monitoring.
| 1F | metadata.json export (browser download) | Serialize form state to metadata.json and trigger browser download. | Form state | metadata.json file in user's Downloads | JS Blob + URL.createObjectURL + anchor download | Canonical hand-off contract into Node 2. No server, no POST.
| 1G | Operator handoff workflow | Document manual steps to move downloaded files (metadata.json + characters.json + sheet PNGs + MP4s) into the pipeline input folder. | All Node 1 outputs | Pipeline input folder ready for Node 2 | README in frontend/ | Browser cannot write directly to disk; manual move is the bridge between frontend and pipeline.
2 |  | Metadata Ingestion & Validation | Load & schema-validate metadata.json + characters.json, confirm every referenced sheet PNG and MP4 exists on disk, and emit an ordered batched queue for Node 3. | Flat input folder: metadata.json + characters.json + sheet PNGs + shot MP4s | queue.json (absolute paths, batched); exit 0/1/2 | Python 3.13 (embedded locally, stdlib on RunPod); pydantic v2 | Locked: runs locally + on RunPod (run_node2.py wrapper); hard-fail whole batch on any error (no per-shot skip); pydantic v2 with extra='forbid'. Each queue.json per-character dict also carries poseExtractor (dwpose / lineart-fallback) from characters.json so Node 7 routes per-character without re-reading characters.json.
| 2A | Parse & schema-validate metadata.json | Load metadata.json via pydantic (MetadataFile). Enforces types, regex on shotId, position enum, fps==25, batchSize 1-64, characterCount == len(characters), bare mp4 filename. | metadata.json | Validated MetadataFile object (or MissingInputError / SchemaValidationError) | pydantic v2 | Rich field-path error messages surface the exact offending field to the operator.
| 2B | Parse & schema-validate characters.json | Load characters.json via pydantic (CharactersFile). Enforces non-empty list, bare sheetFilename, width/height >= 1. Carries angleOrderConfirmed flag through for Node 6. Enforces each character's poseExtractor in {dwpose, lineart-fallback} (defaults to dwpose if absent so libraries saved before the field existed still load). | characters.json | Validated CharactersFile object (or MissingInputError / SchemaValidationError) | pydantic v2 | angleOrderConfirmed defaults to True as of 2026-04-23 (canonical 8-angle order confirmed against Bhim template); Node 6 still hard-fails if an operator deliberately flips it False.
| 2C | Cross-reference checks | (i) every sheetFilename exists in input-dir; (ii) every shot's identity resolves in the character library; (iii) every mp4Filename exists in input-dir. | MetadataFile, CharactersFile, on-disk file listing | Resolved (identity -> CharacterSpec) map (or CrossReferenceError) | Python pathlib | Each failure lists ALL offenders, not just the first, so the operator can fix everything in one pass.
| 2D | Shot-ID integrity | Reject duplicate shotIds and require a contiguous ascending sequence starting at shot_001. | MetadataFile.shots | Pass (or DuplicateShotIdError / ShotIdSequenceError) | Python | Downstream nodes assume the shot_NNN ordering for deterministic filenames; gap/duplicate means silent renumbering later.
| 2E | Build & serialize processing queue | Build ordered ShotJob records (absolute mp4Path + per-character absolute sheetPath + position + durationFrames), chunk into batches of project.batchSize, write queue.json. | Validated MetadataFile + CharactersFile + resolved identity map | queue.json in input-dir (or --output-file) | Python json + dataclasses | CLI exit 0 success, 1 validation (Node2Error), 2 unexpected. queue.json is the contract Node 3 reads.
3 |  | Shot Pre-processing (MP4 -> PNG Sequence) | Decode every queued rough-animatic MP4 into individually-addressable PNG frames (one folder per shot). | queue.json (from Node 2) | Per-shot frame folders + per-shot _manifest.json + aggregate node3_result.json; exit 0/1/2 | Python 3.13 (embedded locally, stdlib + imageio-ffmpeg on RunPod); no GPU imports | Locked: ffmpeg via imageio-ffmpeg wheel (no PATH dep); per-shot folders <work>/<shotId>/frame_NNNN.png; 1:1 decode (no -r); fail-fast on hard errors, warn-and-continue on frame-count drift; core logic in pipeline/node3.py + thin ComfyUI wrapper in custom_nodes/node_03_mp4_to_png/.
| 3A | Load + validate queue.json | Read queue.json; confirm schemaVersion==1, every shot has shotId/mp4Path/durationFrames, no duplicate shotIds, every mp4Path exists on disk. | queue.json path | Validated queue dict (or QueueInputError) | Python json + pathlib | Loud failure on schema drift so Node 2 contract changes never silently half-run Node 3.
| 3B | Per-shot folder setup | Create <work-dir>/<shotId>/ and wipe any stale frame_*.png from prior partial runs. | work_dir path + shotId | Empty frames folder ready for ffmpeg | Python pathlib | Clean slate guarantees _manifest.json matches directory contents exactly.
| 3C | FFmpeg decode | ffmpeg -y -hide_banner -loglevel error -i <mp4> -start_number 1 -vsync 0 <out>/frame_%04d.png. Non-zero exit -> FFmpegError with stderr tail. | MP4 path, empty out_dir | frame_0001.png .. frame_NNNN.png | imageio-ffmpeg (bundled binary) | No -r flag: rough MP4 is already 25 FPS; -r would resample. 1:1 decode is the contract.
| 3D | Frame-count check + sequence verify | Confirm 1..N contiguous numbering (gap -> FrameExtractionError). Compare count to durationFrames; mismatch -> FrameCountWarning (non-fatal). | frames folder; durationFrames from queue.json | Pass / FrameExtractionError / FrameCountWarning record | Python re + glob | Warn-and-continue: Node 9 will use the actual count when rebuilding timing.
| 3E | Write manifests | Write per-shot _manifest.json + top-level node3_result.json aggregating all shots + warnings. Node 4 reads node3_result.json. | Accumulated ShotFrameResult + FrameCountWarning list | <work-dir>/<shotId>/_manifest.json + <work-dir>/node3_result.json | Python json + dataclasses | CLI exit 0 success (warnings are exit 0), 1 Node3Error, 2 unexpected.
4 |  | Key Pose Extraction (Ignore Held Frames) | Partition each shot into key poses (drawing actually changes) + held-frame runs (timing duplicates that do NOT go to the AI generator). Translation-aware: a character sliding across the frame without changing pose stays ONE key pose with per-held-frame (dy, dx) offsets. | node3_result.json (from Node 3) + threshold (float) + max_edge (int) | Per-shot keyposes/frame_NNNN.png copies + per-shot keypose_map.json + aggregate node4_result.json; exit 0/1/2 | numpy (FFT phase correlation) + Pillow (PNG load + LANCZOS downscale); pure-Python, no GPU | Locked: phase correlation + aligned MAE (NOT naive pixel-diff); compare frame-vs-anchor not frame-vs-prev; downscale max edge=128; global threshold default 8.0; no min hold-length; key-pose PNGs COPIED preserving source filenames; core logic in pipeline/node4.py + thin ComfyUI wrapper in custom_nodes/node_04_keypose_extractor/.
| 4A | Load + validate node3_result.json | Check schemaVersion==1, required keys (workDir, shots), every shot has shotId/framesDir/frameFilenames, frames folder exists on disk. Raises Node3ResultInputError on any problem. | node3_result.json path | Validated dict (or Node3ResultInputError) | Python json + pathlib | Distinct from Node 3's QueueInputError so operator can tell "Node 3 never ran" from "Node 4 cannot consume what Node 3 wrote".
| 4B | Per-shot anchor walk + phase correlation | Frame 1 is the first key-pose anchor (downscaled grayscale). For frames 2..N: phase-correlate against the anchor via numpy FFT to estimate (dy_small, dx_small); compute aligned MAE over the valid overlap. | Source frames dir; anchor (downscaled uint8 array); threshold; maxEdge | (dy_small, dx_small, aligned_mae) per frame | numpy.fft.fft2 + Pillow LANCZOS resample | Compare vs current ANCHOR (not N-1) so held-frame offsets are cumulative-from-anchor, which is exactly what Node 9 replays.
| 4C | Classify: held (translated) vs new key pose | If aligned MAE <= threshold, frame is held (offset = [round(dy_small*scale), round(dx_small*scale)] in full-res pixels). Otherwise, frame becomes a new key pose and replaces the anchor. | Aligned MAE + (dy_small, dx_small) + downscale scale factor | HeldFrame or new KeyPoseEntry | Python | No minimum hold-length filter. Even a 1-frame segment between two key poses is its own run.
| 4D | Per-shot output: copy key-pose PNGs + write keypose_map.json | Create <shotId>/keyposes/, wipe stale copies, shutil.copyfile each key-pose frame preserving source filename, write <shotId>/keypose_map.json describing the partition. | Per-shot KeyPoseEntry list; source frames dir | <shotId>/keyposes/frame_NNNN.png copies + <shotId>/keypose_map.json {schemaVersion, shotId, totalFrames, sourceFramesDir, keyPosesDir, threshold, maxEdge, keyPoses: [{keyPoseIndex, sourceFrame, keyPoseFilename, heldFrames: [{frame, offset: [dy, dx]}]}]} | Python shutil + json | Source filenames preserved so Node 9 can cross-reference original frame numbers trivially.
| 4E | Aggregate result | Write <work-dir>/node4_result.json: one ShotKeyPoseSummary per shot (shotId, totalFrames, keyPoseCount, sourceFramesDir, keyPosesDir, keyPoseMapPath) plus run-wide threshold + maxEdge. The contract Node 5 consumes. | Accumulated ShotKeyPoseSummary list | <work-dir>/node4_result.json | Python json + dataclasses | CLI exit 0 success, 1 Node4Error subclass, 2 unexpected.
5 |  | Character Detection & In-Frame Position Analysis | For each key pose, determine which character is where. Angle detection deferred to Node 6 (reference-sheet 8-angle matching). | node4_result.json (Node 4) + queue.json (Node 2) + min_area_ratio + merge_iou | Per-shot <shotId>/character_map.json + aggregate <work-dir>/node5_result.json; exit 0/1/2 | scipy.ndimage.label + binary_erosion (classical CC); numpy (Otsu); Pillow (PNG load). No ML, no GPU. | Locked 2026-04-23: classical CC over ML (no 2GB download per pod; line-art doesn't fit ML training distribution); per-key-pose detection (not per-shot); position bins 25/20/10/20/25 split; Strategy A positional identity zip (v1); warn AND reconcile on count mismatch. Phase 2f (2026-04-28, post-real-shot-debug): the user's storyboard convention puts character outlines at luminance ~0-50 (dark bold black) and BG furniture / safe-area marks at ~80-180 (light grey). The original Otsu binarization (locked decision #1, 2026-04-23) treated all dark-vs-light pixels as one foreground class, which broke when BG lines were drawn — Otsu would either swallow the actual characters into one giant connected component covering 70%+ of the frame OR falsely tag the BG as the character. Phase 2f replaces Otsu with a fixed luminance threshold (default 80, --dark-threshold N to tune) followed by 3x3 morphological closing to seal 1-2 pixel gaps where character outlines crossed BG lines. Side effect: each shot grows a <shot>/dark_lines/<filename>.png per keypose (white BG, black character ink). Node 7's _prepare_rough_bbox_crop reads from dark_lines/ when present (falls back to raw keypose for pre-Phase-2f work dirs), so Flux's VAEEncode + ControlNet operate on character-only pixels. Schema additions are additive: CharacterMap gains darkThreshold + darkLinesDir; Node5Result gains darkThreshold; schemaVersion stays at 1. 70 Node 5 tests pass (+20 new Phase 2f); 479 repo-wide, zero regressions. Otsu function is retained as _binarize_otsu for tests/debugging but no longer wired into _detect_on_key_pose for production. Phase 2f-tuning (2026-05-03, post-live-pod-debug): Phase 2f's 3x3 morphological closing only sealed 1-2 pixel gaps in character outlines, but storyboard art commonly has 5-15 pixel gaps where the artist lifted the pen between strokes (head outline doesn't touch torso, arms don't connect to body). The character then fragmented into 4-6 connected components and Node 5's reconcile dropped the wrong fragments — live-pod test 2026-05-03 on TMKOC EP35 SH004 caught Node 5 detecting bbox=178 px tall (25% of frame) when the actual character was ~430 px tall (60% of frame). Phase 2f-tuning shipped _detect_bboxes_adaptive: iterative dilation BEFORE CC, trying levels [0, 1, 2, 3, 5, 7, 10, max_dilation] and stopping at the first level where significant-blob count <= metadata's expected_count. Adapts naturally to camera framing — wide shots small characters need 0-2 dilations, close-ups large characters need 8-15. CLI flag --bbox-max-dilation N (default 15) caps the iteration count. New bbox-adaptive-dilation warning records the chosen level per-keypose. Schema additions are additive: CharacterMap + Node5Result gain bboxMaxDilation: int = 15 (defaults fill in for old manifests; schemaVersion stays at 1). 7 new tests; 77 total Node 5 tests; 500 repo-wide, zero regressions.
| 5A | Load + validate inputs | Read node4_result.json + queue.json; check schemaVersion==1 + required keys; build shotId->[{identity, position}] lookup from queue.batches. Missing shotIds raise QueueLookupError. | node4_result.json path; queue.json path | Validated dicts + character lookup (or Node4ResultInputError / QueueLookupError) | Python json + pathlib | Distinct from Node 4's Node3ResultInputError so operator can tell 'Node 4 never ran' from 'Node 5 cannot consume what Node 4 wrote'.
| 5B | Per-key-pose connected-component detection | Load key-pose PNG as grayscale, apply Otsu binarization (foreground = dark ink), run scipy.ndimage.label with 8-connectivity, drop blobs below min_area_ratio*frame_area, merge bboxes with IoU>=merge_iou. | Key-pose PNG path; min_area_ratio (default 0.001); merge_iou (default 0.5) | List of (x, y, w, h, area) bboxes + reconcile-dropped/reconcile-merged warnings | numpy (Otsu inline); scipy.ndimage.label + find_objects | 8-connectivity (diagonals count). Otsu is adaptive so paper/ink tone variation across shots is handled. IoU merge reunites floating details (eye drawn as separate blob) with parent silhouette. Phase 2f (2026-04-28): replaced Otsu binarization with _extract_dark_lines (fixed luminance threshold, default 80) + _close_outline_gaps (3x3 morphological closing) before the CC step. Otsu is retained as _binarize_otsu for tests but no longer wired into the production path. Side-effect _save_dark_lines_png writes <shot>/dark_lines/<filename>.png per keypose for Node 7 to consume — gives Flux character-only pixels with BG furniture erased to white. _wipe_dark_lines_dir handles rerun safety (removes stale *.png, leaves non-PNG files alone for operator debug notes). All four helpers exported in __all__. Phase 2f-tuning (2026-05-03): replaced _detect_bboxes (single dilation pass) with _detect_bboxes_adaptive (iterative dilation toward expected_count from metadata) for the production path. _detect_bboxes is retained for tests. Adapts to character size on canvas — small wide-shot characters get 0-2 dilations; large close-up characters get 8-15. CLI flag --bbox-max-dilation N (default 15) caps iteration count.
| 5C | Reconcile count against metadata | Compare blob count to len(shot.characters). Too-many -> keep top-N largest by area (count-mismatch-over warning). Too-few -> progressive binary_erosion x1/x2/x3 until count matches (reconcile-eroded warning). Still-wrong -> reconcile-failed warning; Node 6 fails cleanly. | Detected bboxes; expected count; binary mask | Reconciled bboxes list + DetectionWarning records | scipy.ndimage.binary_erosion | Warn AND reconcile, never fail-fast (locked). Max 3 erosion iterations before giving up - beyond that we're eroding away legitimate character features.
| 5D | Position binning | Compute each bbox's normalized centre-x and bucket into L/CL/C/CR/R via 25/20/10/20/25 thresholds: [0.00,0.25) L, [0.25,0.45) CL, [0.45,0.55) C, [0.55,0.75) CR, [0.75,1.00] R. | Bbox list; frame width | Per-bbox positionCode + centerX (normalized) | Python | C is a narrow 10% exact-centre band; L and R are 25% each. Same thresholds every shot - no operator knob.
| 5E | Identity assignment (Strategy A) + manifest write | Sort detections left->right by centre-x; sort metadata by position rank (L<CL<C<CR<R, tiebreak on metadata order); zip. Write <shotId>/character_map.json (next to keyposes/) + aggregate <work-dir>/node5_result.json. | Bboxes + positions; shot.characters metadata list | <shotId>/character_map.json {schemaVersion, shotId, expectedCharacterCount, expectedCharacters, keyPoses:[{keyPoseIndex, sourceFrame, frameWidth, frameHeight, detections, warnings}]} + aggregate node5_result.json | Python dataclasses + json | Strategy A (positional) for v1. If real mismatch rates > 5%, add v2 Strategy B (reference-sheet-similarity verification) as post-pass without replacing Strategy A. Extra unmatched bboxes carry identity='' for operator review.
6 |  | Character Reference Sheet Matching | For each character Node 5 detected in each key pose, pick the best-matching 8-angle view from the model sheet and emit it as a BnW line-art crop ready for Node 7 IP-Adapter / Reference-Only conditioning. | node5_result.json (Node 5) + queue.json (Node 2) + characters.json (Node 1) + sheet PNGs referenced from queue | Per-shot <shotId>/reference_map.json + <shotId>/reference_crops/<identity>_<angle>.png + _lineart.png + aggregate <work-dir>/node6_result.json | Pillow (RGBA + alpha slicing) + scipy.ndimage (CC label) + numpy (Otsu + DoG + IoU/symmetry scoring); pure-Python, CPU-only | Locked 2026-04-23: require alpha on sheet (fail loud); canonical 8-angle order confirmed against Bhim template; structured-fail on angleOrderConfirmed=false; classical shape-similarity (IoU + symmetry + aspect + edge density) over ML; recompute silhouette in Node 6 (no Node 5 retro-change); DoG line-art (sigma1=1.0, sigma2=2.0); per-key-pose granularity; Option C thin ComfyUI wrapper; no new Python deps; characters.js now defaults angleOrderConfirmed=true. Phase 2g (2026-05-03, post-live-pod-debug locked decisions): default angle_mode flipped from 'auto' (multi-signal silhouette scoring across all 8 angles) to 'front-only' (always pick 'front'). Reason: IP-Adapter needs the character's FACE for identity learning; back-view crops give it nothing useful. Live-pod test 2026-05-03 on TMKOC EP35 SH004 caught Node 6's 'auto' mode picking back-3q-R (TAPPU from behind) for a front-facing rough — silhouette IoU happened to score highest on the fragmented Node 5 silhouette. IP-Adapter then had only the back of TAPPU's head as the identity reference and produced generic bald-old-man instead of TAPPU. Multi-signal scoring is RETAINED as opt-in via --angle-mode auto. CLI flag --angle-mode {auto, front-only}. New phase2g_override marker in scoreBreakdown records when the override fires. Schema additions: Node6Result gains angleMode: str = 'front-only' (additive; schemaVersion stays at 1). 9 new tests + 1 modified angle test; 43 total Node 6 tests; 500 repo-wide, zero regressions.
| 6A | Load + validate inputs | Read node5_result.json + queue.json + characters.json. Check all schemaVersion==1. Build shotId -> [{identity, sheetPath}] lookup. Enforce characters.conventions.angleOrderConfirmed==true (else AngleOrderUnconfirmedError). Raise Node5ResultInputError / QueueLookupError / CharactersInputError on malformed manifests or stale references. | node5_result.json path; queue.json path; characters.json path | Validated dicts + character/sheet lookup (or typed Node6Error subclass) | Python json + pathlib | QueueLookupError reused from Node 5 with identical semantics (same PipelineError root).
| 6B | Slice + cache reference sheets | Per unique identity: load sheetPath as RGBA; raise ReferenceSheetFormatError if not RGBA; scipy.ndimage.label on alpha>0; verify bbox count==8 (else ReferenceSheetSliceError); cache crops keyed by (identity, angle_name) matching characters.conventions.angleOrderLeftToRight. Convert each color crop to line art via DoG (sigma1=1.0, sigma2=2.0, OR-combined with alpha boundary). Write color + line-art PNGs to <shotId>/reference_crops/<identity>_<angle>.png / _lineart.png. | Sheet PNG per unique character; angle-name list from characters.json | <shotId>/reference_crops/<identity>_<angle>.png + _lineart.png; in-memory (color, line-art) crop cache | Pillow (RGBA + alpha) + scipy.ndimage.label + numpy DoG | Alpha channel is the authoritative silhouette; gating RGB-only sheets prevents Otsu fallback ambiguity.
| 6C | Recompute silhouette per key-pose detection | For each detection in every key-pose character_map.json: crop the key-pose PNG to the detection boundingBox; Otsu binarize; keep largest connected component as the rough silhouette mask. | Key-pose PNG path + detection boundingBox | Binary silhouette mask per detection | Pillow + numpy Otsu + scipy.ndimage.label | Reuses the Otsu approach from Node 5 5B; edge case (Node 5 reconcile-eroded detections) tolerated given 8-way matching is coarse.
| 6D | Angle matching (classical multi-signal score) | Scale-normalize rough silhouette + 8 reference alpha-silhouettes to a 128x128 centered-on-centroid canvas (aspect-preserving pad). Score each (rough, reference) pair via weighted combination of: silhouette IoU, horizontal-symmetry score, bbox aspect-ratio similarity, interior-edge density in upper head band. Pick max-score angle. | Rough silhouette mask + 8 reference silhouettes + original key-pose crop (for interior edges) | Selected angle name + score breakdown per detection | numpy + Pillow | No ML/CLIP/pose-model in v1. Interior edge density breaks front/back silhouette tie (face lines present on front, absent on back). Weights + sigmas tuned at code-time against the Bhim smoke fixture. Phase 2g (2026-05-03): multi-signal scorer is retained for --angle-mode auto, but production default is 'front-only' which overrides best_idx to the index of the 'front' angle in sheet_crops. Reason: IP-Adapter needs the character's face for identity learning; back-view crops produce generic character output. CLI flag --angle-mode {auto, front-only}. The override leaves a phase2g_override='front' marker in scoreBreakdown.
| 6E | Emit reference_map.json + aggregate node6_result.json | Per shot write <shotId>/reference_map.json: per key pose per detection {identity, selectedAngle, scoreBreakdown, referenceColorCropPath, referenceLineArtCropPath}. Aggregate <work-dir>/node6_result.json: one ShotReferenceSummary per shot (shotId, keyPoseCount, referenceMapPath, angleHistogram). Node 7 reads reference_map.json directly. | Accumulated per-key-pose angle selections + crop paths | <shotId>/reference_map.json; <work-dir>/node6_result.json | Python json + dataclasses | CLI exit 0 success, 1 Node6Error subclass, 2 unexpected. reference_map.json is the contract Node 7 consumes.
7 |  | AI-Powered Pose Refinement (Replace Rough With BnW Line Art) | Generate clean BnW line-art of the correct character in the same pose as the rough sketch. Pose comes from the rough (action-accurate) via DWPose (humans) or LineArt/Scribble fallback (non-humans). Identity comes from Node 6's color reference crop via IP-Adapter. Txt2img so rough pixels do not bleed through. | node6_result.json + queue.json (for per-character poseExtractor) + Node 6's color reference crops + rough key-pose PNGs + pinned SD checkpoint / CN / IP-Adapter weights | Per-character refined BnW line-art PNGs on transparent background + per-shot refined_map.json + aggregate node7_result.json | ComfyUI workflow JSON + thin custom-node wrapper (breaks pipeline/node*.py template on purpose); SD 1.5 + AnyLoRA line-art checkpoint + optional BnW LoRA; DWPose preprocessor + DWPose CN; LineArt + Scribble CN (non-human fallback); IP-Adapter-Plus; RunPod-only | Locked 2026-04-23: separate pose (from rough skeleton) from identity (from Node 6 reference crop); per-character poseExtractor routing via characters.json (dwpose default for humans, lineart-fallback for non-humans like Jaggu); IP-Adapter fed the COLOR reference crop; txt2img (not img2img) so rough pixels do not bleed; per-character generation then Node 8 composites; SD 1.5 + AnyLoRA + optional BnW LoRA; DPM++ 2M Karras 25 steps CFG 7.0 512x512; seed logged per (shotId, keyPoseIndex, identity); RunPod-only (no local VRAM for full stack); ComfyUI-Manager for dev convenience + curl+SHA pins in runpod_setup.sh + models.json for production; no QC v1 -- metadata logging only, retry is a future Node 11C hook; transparent-background PNG output. Runtime topology: ComfyUI runs on the RunPod pod, not the laptop; laptop produces Nodes 2-6 outputs via CPU-only CLIs and syncs the work-dir to the pod; on the pod runpod_setup.sh symlinks custom_nodes/node_07_pose_refiner into ComfyUI and curl-downloads models.json pins; `python run_node7.py` runs on the pod and POSTs workflow.json to ComfyUI's HTTP API; local ComfyUI_windows_portable is for Nodes 3-6 wrapper authoring/smoke-tests only (insufficient VRAM for Node 7's SD 1.5 + ControlNet + IP-Adapter + DWPose stack). Status (2026-04-24): DONE -- scaffold shipped. 47 tests pass (207 repo-wide). Files: pipeline/cli_node7.py + run_node7.py + custom_nodes/node_07_pose_refiner/{__init__.py, manifest.py, comfyui_client.py, orchestrate.py, workflow.json, workflow_lineart_fallback.json, models.json, README.md} + runpod_setup.sh (extended with custom-node clone + curl weight download + sha256 verify) + tests/test_node7.py. Typed errors: Node7Error base + Node6ResultInputError + RefinementGenerationError + WorkflowTemplateError + ComfyUIError (QueueLookupError reused from Node 5). CLI exit 0 success (per-generation errors still exit 0), 1 (Node7Error, QueueLookupError) whole-run failure, 2 unexpected. Live RunPod run pending first execution (ComfyUI contact + real weights). Status (2026-04-25): DONE - both routes live-verified on RunPod. First live run (lineart-fallback both characters): 2 generated / 0 skipped / 0 error, 36s wall time, 2-character synthetic smoke fixture. DWPose verification (same fixture, Bhim flipped to dwpose, Jaggu still lineart-fallback): 2 generated / 0 skipped / 0 error, 41s wall time, both routes in the same Node 7 invocation; per-character routing table works; Bhim PNG bytes differ from baseline (sha d77d9b18.. vs 038f69e6..) confirming DWPose contributes pose info; Jaggu PNG bytes are bit-identical (sha 5aa3c619..) confirming the deterministic-seed contract holds for unchanged routes. Runpod-slim pod image needed FOUR bringup steps (symlink comfyui_controlnet_aux, write extra_model_paths.yaml, add weight_type: standard to both workflow JSONs, pip-install matplotlib + scikit-image + onnxruntime into the venv for DWPose) - all captured in tools/POD_NOTES_runpod_slim.md and the Node 7 - live-run addendum of CLAUDE.md. Phase 2 (Flux migration) — design-locked 2026-04-26, code not yet shipped. Real-shot TMKOC test (EP35 SH004) succeeded mechanically end-to-end in 33.8s on the 4090 but produced anime-girl output instead of TMKOC characters because SD 1.5 + AnyLoRA is anime-trained. Hug-test proof-of-concept (Flux Dev fp8 + Flat Cartoon Style v1.2 + ControlNet Union Pro + DWPose + txt2img, single generation, no IP-Adapter) on the same pod generated dramatically better output (~70s on the 4090) — recognizable Tappu + Champak Lal in TMKOC style. 14 architectural decisions locked across CLAUDE.md 'Node 7 v2 — locked decisions' + PLAN.md 'NODE 7 v2': (1) Flux Kontext Dev fp16 base; (2) Flat Cartoon Style v1.2 LoRA @ 0.75, replaced by custom-trained TMKOC v1 in Phase 2d; (3) ControlNet Union Pro (single CN, routes via SetUnionControlNetType) @ 0.65; (4) XLabs Flux IP-Adapter v2 @ 0.8 (requires x-flux-comfyui custom node); (5) img2img with denoise=0.55 (REVERSES Phase 1 txt2img — Flux Kontext Dev's superior denoising resolves the rough-pixel-bleed concern); (6) CN 0.65 + IP-Adapter 0.8; (7) 1280x720 native (matches source MP4); (8) dpmpp_2m_sde + simple + 40 steps + FluxGuidance 4.0 + CFG 1.0; (9) per-character LoRAs Phase 2e — plan architecture, defer training, bootstrap data via Phase 2b IP-Adapter, ai-toolkit (ostris) on A100 80GB ~$5-15 + 1.5h per character; (10) backward-compat: schemaVersion stays 1, all changes additive; (11) A100 80GB + Flux Dev fp16 default, fp8 fallback via --precision flag; (12) Phase 1 weights archived (deprecated:true, removal scheduled 2026-10-26); (13) architecture template unchanged (workflow JSON + thin custom-node wrapper, no pipeline/node7.py); (14) failure mode unchanged (log + continue, no QC gate in v1; future Node 11C retry hook is the right home for operator-level retries). Implementation roadmap rows 71-77 (sub-steps 7v2-A through 7v2-G). Hug-test workflow JSON at _pod_out/flux_tmkoc_test_workflow.json is the implementation starting point for workflow_flux_v2.json.
| 7A | Load + validate inputs | Read node6_result.json + queue.json; check schemaVersion==1; build (shotId, keyPoseIndex, identity) -> (referenceColorCropPath, poseExtractor) lookup. Raise Node6ResultInputError / QueueLookupError on manifest problems. | node6_result.json path; queue.json path | Validated dicts + per-detection routing table (or typed Node7Error subclass) | Python json + pathlib | Same validate-up-front pattern as Nodes 3/4/5/6 -- loud failure on schema drift. Shipped in pipeline/cli_node7.main + custom_nodes/node_07_pose_refiner/orchestrate.py (load_node6_result + load_queue + build_pose_extractor_lookup + build_routing_table).
| 7B | Pose conditioning (per-character, routed) | Crop rough key-pose PNG to Node-5 bbox with margin. If poseExtractor=='dwpose': run DWPose preprocessor -> skeleton -> DWPose ControlNet at strength 0.75. If poseExtractor=='lineart-fallback': feed rough crop through LineArt + Scribble CN at strength 0.6 each instead. | Rough key-pose PNG + Node-5 bbox + character poseExtractor route | Pose CN conditioning tensor (skeleton or lineart/scribble) | ComfyUI DWPose preprocessor + DWPose CN; LineArt CN; Scribble CN | DWPose handles stylized cartoon human proportions better than classical OpenPose. Quadrupeds (Jaggu) lack a reliable skeleton so they route through the lineart-fallback stack; every character still has a model sheet for identity. Shipped via two workflow JSON templates routed per-detection by orchestrate.py: workflow.json (DWPose: nodes 40 DWPreprocessor + 41 ControlNetApplyAdvanced @ 0.75 + 42 ControlNetLoader control_v11p_sd15_openpose.pth) vs workflow_lineart_fallback.json (LineArtPreprocessor + Scribble CN stack @ 0.6 each).
| 7C | Identity conditioning (IP-Adapter) | Load Node 6's COLOR reference crop (not the DoG line-art) into IP-Adapter-Plus at strength 0.8. Reference-Only CN available as a secondary tiebreaker at lower priority. | Node 6's referenceColorCropPath for (identity, angle) | Identity conditioning tensor | ComfyUI IP-Adapter-Plus + Reference-Only CN | IP-Adapter expects a textured/colored image for its identity embedding; the DoG line-art crop is available for Reference-Only fallback but not the primary identity channel. Shipped in both workflow templates: IPAdapterUnifiedLoader node 50 (PLUS high strength) + IPAdapter node 51 @ weight 0.8 fed from node 12 LoadImage (Node 6 color reference crop).
| 7D | Generation (SD 1.5 + line-art checkpoint) | SD 1.5 + AnyLoRA (line-art-tuned) + optional BnW LoRA. DPM++ 2M Karras, 25 steps, CFG 7.0, 512x512. Txt2img only -- no img2img bleed-through. Seed logged per (shotId, keyPoseIndex, identity) so a failed retry can be re-run deterministically. | Pose CN + Identity CN from 7B/7C | Raw generated RGB image | SD 1.5 + AnyLoRA line-art checkpoint + optional BnW LoRA | Shot's multiple key poses share a seed base for visual coherence within the shot. Exact checkpoint + LoRA pinned in custom_nodes/node_07_pose_refiner/models.json + runpod_setup.sh. Shipped in both workflow templates: node 3 KSampler with DPM++ 2M Karras, 25 steps, CFG 7.0, 512x512 EmptyLatentImage (node 5). Seed derived deterministically from SHA256(project¦shotId¦keyPoseIndex¦identity) masked to 31 bits (orchestrate._derive_seed).
| 7E | Post-process to BnW alpha PNG | Luminance-threshold the generated RGB to pure BnW; build alpha mask from the skeleton/lineart regions; write a transparent-background 512x512 PNG to <shotId>/refined/<keyPoseIndex>_<identity>.png. | Raw generated RGB image | <shotId>/refined/<keyPoseIndex>_<identity>.png | numpy + Pillow (luminance threshold + alpha build) | Transparent-background output gives Node 8's compositor clean alpha to place each character onto the final frame canvas. Shipped in both workflow templates: node 20 SaveImage with filename_prefix animatic/refined; orchestrate.extract_first_image downloads the PNG via ComfyUI /view and writes to <shotId>/refined/<NNN>_<identity>.png.
| 7F | Emit manifest | Write per-shot <shotId>/refined_map.json: every generated character (sourceKeyPoseFrame, identity, angle, seed, refinedPath, poseExtractor used, CN strengths). Aggregate <work-dir>/node7_result.json: ShotRefinedSummary per shot. Node 8 reads refined_map.json directly. | Accumulated generation records | <shotId>/refined_map.json + <work-dir>/node7_result.json | Python json + dataclasses | CLI exit 0 success (per-generation skips are still exit 0), 1 Node7Error subclass, 2 unexpected. No auto-retry / QC gate in v1 -- metadata only; retries are a future Node 11C hook. Shipped in custom_nodes/node_07_pose_refiner/manifest.py: write_refined_map (per-shot) + write_node7_result (aggregate, stamps refinedAt UTC). Dry-run marks every generation status=skipped; live run marks failures status=error and CLI still exits 0.
8 |  | Scene Assembly (Per Key Pose Frame) | Produce the finished, fully-composed refined key pose frame. | Per-character refined outputs | One clean composite PNG per key pose | PIL / ComfyUI compositor | Status (2026-04-25): DONE - design-locked + shipped same day. pipeline/node8.py + pipeline/cli_node8.py + run_node8.py + custom_nodes/node_08_scene_assembler/__init__.py + tests/test_node8.py (51 tests pass, 258 repo-wide). Pure-Python PIL+numpy, no GPU, no new deps. Bbox is single source of truth (Node 5 wrote, Node 7 cropped, Node 8 places back). Feet-pinned scaling: feet land at bbox.bottomY within +/-2 px LANCZOS tolerance, never in the bbox middle. White canvas at source MP4 res, z-order by bbox.bottomY ascending, BnW threshold (no dilate/erode normalize in v1). Substitute-rough fallback on Node 7 status=error or empty-refined-PNG: warn and exit 0; only an unfillable slot (refined dead AND rough also dead) raises RefinedPngError. Rerun wipes <shotId>/composed/ first. Output is still only key poses - held frames added in Node 9.
| 8A | Place refined characters at correct positions | Load + validate node7_result.json (schemaVersion==1). For each shot chase pointers to refined_map.json, character_map.json (Node 5), keypose_map.json (Node 4). Probe one frame_NNNN.png per shot for original (W, H). | node7_result.json (--node7-result path); per-shot refined/character/keypose maps; one Node 3 frame for dims | Validated in-memory shot list with bboxes, refined PNG paths, source frame dims | Python stdlib (json), PIL (probe dims) | Raises Node7ResultInputError on any structural problem. Locked decision #1 (bbox = single source of truth).
| 8B | Per-key-pose canvas build | Create (W, H) RGB white canvas per key pose, where (W, H) is the source MP4 resolution probed in 8A. | Source frame dims from 8A | Blank RGB white canvas per key pose, ready for character paste | PIL.Image.new | Locked decisions #3 (canvas = source MP4 res) + #4 (background = solid white).
| 8C | Per-character paste (feet-pinned) | For each character with status==ok: open 512x512 refined PNG, find lowest non-white pixel = feet_y_in_512, compute scale = bbox.height / (feet_y_in_512 - top_y_in_512), resize aspect-preserving, threshold to BnW, paste centered on (bbox.centerX, bbox.bottomY). For status!=ok: copy rough key-pose pixels in the bbox region (substitute-rough) + warn. | Refined 512x512 PNGs (Node 7), Node 5 bboxes, rough key-pose PNG (Node 3/4) for substitute fallback | Characters pasted onto the canvas; warnings for any substitute-rough events | PIL (open, resize, paste, threshold), numpy (find non-white pixel) | Locked decisions #2 (feet-pinned scaling, NOT stretch-to-fit) + #6 (BnW threshold only) + #7 (substitute-rough on Node 7 errors).
| 8D | Z-order resolution | Sort detections per key pose by bbox.bottomY ascending and paste in that order so lower-on-screen characters land last (drawn on top). | Per-key-pose detection list with bboxes | Z-ordered paste sequence (input to 8C) | Python sorted(), no deps | Locked decision #5 (z-order = bbox.bottomY descending). 8D actually feeds 8C — the order they're listed is editorial; the code does z-sort then paste.
| 8E | Emit composed PNGs + manifests | Write <shotId>/composed/<keyPoseIndex>_composite.png (RGB, source MP4 res, white bg, no alpha), per-shot composed_map.json, and the aggregate <work-dir>/node8_result.json. | Composited canvas from 8B+8C+8D | <shotId>/composed/*_composite.png + composed_map.json + node8_result.json | PIL (save), Python json | Locked consequences: composed_map.json is Node 9's contract. Output is RGB no-alpha. Rerun wipes <shotId>/composed/ first so manifest always matches dir exactly.
9 |  | Timing Reconstruction (Re-apply Held Frames) | Rebuild the full-length sequence using the timing map from Node 4. | Refined key poses; timing_map.json | Full-length refined PNG sequence | Python | Status (2026-04-25): DONE - design-locked + shipped same day. pipeline/node9.py + pipeline/cli_node9.py + run_node9.py + custom_nodes/node_09_timing_reconstructor/__init__.py + tests/test_node9.py (42 tests pass, 300 repo-wide). Pure-Python PIL+numpy, no GPU, no new deps. Translate-and-copy on a fresh white canvas: anchor frames are bit-identical pixel copies of Node 8's composite; held frames are pasted at (dx, dy) offset from keypose_map.json onto fresh white canvas, exposed regions stay white. Whole-frame translation (per-character placement is already baked into Node 8's composite). Off-canvas translates are NOT errors (mathematically valid for end-of-slide shots; produces mostly-white frame). Hard-fails on missing composed PNG (TimingReconstructionError), totalFrames mismatch (FrameCountMismatchError), and Node 4 invariant violations like duplicate frame indices or out-of-range frames (KeyPoseMapInputError). Rerun wipes <shot>/timed/ first. CLI: --node8-result only (chases composed_map.json -> shot root -> keypose_map.json). Output is full per-frame sequence ready for Node 10 to encode back to MP4.
| 9A | Load + validate inputs | Read node8_result.json (schemaVersion==1), chase pointers to per-shot composed_map.json + sibling keypose_map.json. Validate Node 4 invariants: every frame index appears exactly once, all in [1, totalFrames], no duplicate keyPoseIndices. | node8_result.json (--node8-result); per-shot composed_map.json; per-shot keypose_map.json | Validated in-memory shot list with per-frame (keyPoseIndex, offset, isAnchor) lookup | Python stdlib (json, pathlib) | Raises Node8ResultInputError or KeyPoseMapInputError on structural problems. Locked decisions #6 (single --node8-result) + #10 (duplicate frame index = hard error).
| 9B | Map key poses to timing slots | Build per-shot frame_index -> (keyPoseIndex, offset_dy_dx, isAnchor) lookup so each frame resolves directly to source composite + translation in O(1). | Validated keypose_map.json from 9A | Per-frame source-composite + offset lookup table | Python dict | Pure data-shape transform; no I/O.
| 9C | Translate-and-copy per frame | For each frame_index in 1..totalFrames: open source composite (cached per keyPoseIndex within a shot), build fresh white canvas at composite's (W, H), paste composite at offset (dx, dy). Anchor frames (offset==[0,0]) are bit-identical copies of Node 8's composite. | Per-frame lookup from 9B; Node 8 composite PNGs from <shot>/composed/ | <shot>/timed/frame_NNNN.png (RGB, source MP4 res, white bg) | PIL.Image.new + paste; per-keyPoseIndex composite cache | Locked decisions #1 (translate-and-copy on white canvas, NO AI), #2 (whole-frame translation, not per-character), #4 (white fill), #9 (off-canvas translates are NOT errors).
| 9D | Assemble + verify | Count <shot>/timed/frame_*.png files; must equal keypose_map.totalFrames. Mismatch raises FrameCountMismatchError with shot ID + expected/actual counts. | <shot>/timed/ directory + keypose_map.totalFrames | Per-shot pass/fail check; raises on mismatch | Path.glob | Locked decision #8 (totalFrames mismatch is a hard error). Defends against silent Node 4 bugs.
| 9E | Emit manifests | Write <shotId>/timed_map.json (per-frame record: frameIndex, sourceKeyPoseIndex, offset, composedSourcePath, timedPath, isAnchor) and aggregate <work-dir>/node9_result.json (per-shot summary). | Outputs from 9C + 9D | <shotId>/timed_map.json + node9_result.json | Python json | timed_map.json is Node 10's contract. Rerun wipes <shot>/timed/ first so the manifest always matches the dir exactly. Locked decisions #5 (1-indexed 4-digit numbering) + #13 (rerun safety).
10 |  | Output Generation (PNG -> MP4) | Encode the final refined PNG sequence back into an MP4. | Final PNG sequence | shot_XXX_refined.mp4 | FFmpeg | Status (2026-04-25): DONE - design-locked + shipped same day. pipeline/node10.py + pipeline/cli_node10.py + run_node10.py + custom_nodes/node_10_png_to_mp4/__init__.py + tests/test_node10.py (42 tests pass, 342 repo-wide). Pure-Python subprocess + imageio_ffmpeg + json. No GPU, no new deps. ffmpeg via imageio-ffmpeg static binary; codec H.264 (libx264) + yuv420p + medium preset + CRF 18 default + 25 FPS hardcoded. Output to <work-dir>/output/<shotId>_refined.mp4. Post-encode verification via imageio_ffmpeg.count_frames_and_secs (catches silent ffmpeg corruption: exit 0 but malformed file). Odd canvas dims fail-loud (libx264 requires even W/H; auto-padding would silently desync Node 9 positions). Does NOT delete upstream artifacts (intermediates kept for debugging + Part 2 ToonCrafter reuse). Rerun is atomic via ffmpeg -y flag. Multi-shot batches encode each into the same output/ directory.
| 10A | Load + validate inputs | Read node9_result.json (schemaVersion==1), chase pointers to per-shot timed_map.json, verify per-shot <shot>/timed/ directory exists with the expected frame_NNNN.png count. | node9_result.json (--node9-result); per-shot timed_map.json; per-shot timed/ directory | Validated in-memory shot list with timed-dir paths and expected frame counts | Python stdlib (json, pathlib) | Raises Node9ResultInputError or TimedFramesError on structural problems. Locked decision #15 (single --node9-result CLI flag).
| 10B | Probe canvas dimensions | Open one PNG per shot (frame_0001.png), read (W, H). If either is odd, raise FFmpegEncodeError with a clear 'libx264 requires even dimensions' message. Operator re-encodes source MP4 with even dimensions. | <shot>/timed/frame_0001.png (probe target) | Per-shot (W, H) tuple; or FFmpegEncodeError on odd dims | PIL.Image.open + .size | Locked decision #11 (odd dims = hard error, NOT auto-pad). Auto-padding would shift every character by half a pixel and silently desync Node 9 positions.
| 10C | ffmpeg encode | ffmpeg -y -hide_banner -loglevel error -framerate 25 -i <shot>/timed/frame_%04d.png -c:v libx264 -pix_fmt yuv420p -crf <crf> -preset medium <work>/output/<shotId>_refined.mp4. Non-zero exit raises FFmpegEncodeError with last 10 stderr lines. | <shot>/timed/frame_*.png + canvas dims from 10B + CRF (default 18) | <work-dir>/output/<shotId>_refined.mp4 (H.264, yuv420p, 25 FPS) | imageio_ffmpeg static binary + subprocess | Locked decisions #1 (imageio-ffmpeg, not system) + #2 (libx264) + #3 (yuv420p) + #4 (CRF 18) + #5 (preset medium) + #6 (25 FPS hardcoded) + #7 (output to <work>/output/) + #8 (filename pattern <shotId>_refined.mp4) + #17 (-y overwrite for rerun safety).
| 10D | ffprobe verification | ffprobe -v error -select_streams v:0 -show_entries stream=codec_name,r_frame_rate,nb_frames -of json <output.mp4>. Parse JSON; require codec_name==h264, r_frame_rate parses to 25.0 +/-0.01, nb_frames matches input PNG count within +/-1. Mismatch raises FFmpegEncodeError. | <output.mp4> from 10C + expected PNG count from 10A | Pass/fail check; ffprobe parsed metadata for the aggregate manifest | imageio_ffmpeg + subprocess + json | Locked decision #9 (catches silent ffmpeg corruption: exit 0 but malformed file). Cheap (~50ms per shot).
| 10E | Emit aggregate manifest | Write <work-dir>/node10_result.json listing every shot's {shotId, outputPath, frameCount, durationSeconds, codec, fps, fileSizeBytes}. No per-shot manifest beyond this entry - Node 10's output is the deliverable itself, not a pointer. | Verified outputs from 10D | <work-dir>/node10_result.json | Python json | Locked decision #10 (do NOT delete upstream artifacts - intermediates stay for debugging + Part 2 ToonCrafter reuse). Node 10 is purely additive.
11 |  | Batch Management | Keep the pipeline moving shot-by-shot across the whole batch. | Processing queue | Completed batch + report | Python orchestrator | Status (2026-04-25): DONE - design-locked + shipped same day. pipeline/node11.py + pipeline/cli_node11.py + run_node11.py + custom_nodes/node_11_batch_manager/__init__.py + tests/test_node11.py (46 tests pass, 388 repo-wide). Pure-Python orchestrator subprocess + json + datetime. No GPU, no new deps. Subprocess-invokes run_nodeN.py for N in 2..10 in sequence; per-node retry via --retry-nodeN <int> (default 0); pre-Node-7 best-effort nvidia-smi (warn-and-proceed); JSONL progress log + final aggregate report; partial-success semantic = exit 0 with failedShots in JSON; 100% failure = BatchAllFailedError exit 1; --dry-run propagates to Node 7. With Node 11 shipped, the entire 11-node pipeline is end-to-end complete. Live RunPod verification (2026-04-25, RTX 4090): 1 shot succeeded / 0 failed in 33.8s end-to-end via single run_node11.py call. Per-node: Nodes 2-6 + 8-10 each <1s; Node 7 LIVE SD generation (lineart-fallback) dominated at 30.4s; orchestration overhead ~2s. Pre-Node-7 nvidia-smi check fired correctly. Bringup gap caught: system python3 needs pipeline/requirements.txt installed (the runpod-slim venv has Comfy's deps but the system Python doesn't until pip install -r requirements.txt). Captured in tools/POD_NOTES_runpod_slim.md (new step 5).
| 11A | Pre-flight checks | Verify --input-dir exists + readable; load metadata.json + characters.json minimally to confirm well-formed; if Node 7 will be live (not --dry-run), shell-out to nvidia-smi and log GPU info (warn but proceed if not available). | --input-dir <path>; --dry-run flag | Validated input dir; logged GPU info (or warning); InputDirError on bad inputs | Python pathlib + json + subprocess (nvidia-smi best-effort) | Locked decision #7 (best-effort GPU check, NOT a hard gate). Catches 'operator forgot to set up the pod' before Node 7 burns minutes.
| 11B | Sequential per-node execution | For each node N in 2..10: build the appropriate run_nodeN.py argv with chained --node{N-1}-result paths, spawn subprocess with stdout/stderr passthrough + JSONL tee, time it, capture exit code. On non-zero exit: retry up to --retry-nodeN times (default 0). On final non-zero: record as failed. | Validated input from 11A + per-node retry overrides | All Node 2-10 outputs on disk + per-(shotId, nodeN, attempt) JSONL events | Python subprocess (no capture; passthrough) + json (tee to JSONL) | Locked decisions #1 (subprocess, NOT in-process import), #5 (default retries=0), #6 (per-node retry override), #10 (real-time stdout passthrough + JSONL tee).
| 11C | Per-shot status tracking | Aggregate per-shot per-node status by reading downstream nodes' own per-shot manifests. A shot is 'succeeded' iff <shotId>_refined.mp4 exists in <work-dir>/output/ after Node 10; otherwise 'failed', with the failing node number recorded. | Per-shot manifests from Nodes 2-10 + final output/ directory | Per-shot status dict {shotId: {status, failingNode, nodeStatuses[], refinedMp4Path}} | Python json + pathlib | Locked decision #11 (final report aggregates by reading downstream manifests, not by mutating during 11B's run loop). Cleanly separates 'run the nodes' from 'compute the report'.
| 11D | Final report | Write <work-dir>/node11_result.json with per-shot per-node status + timing + final-MP4 path + total batch wall time. Stdout summary: [node11] OK - N shots / M succeeded / K failed, total Xs, MP4s in <output_dir>/. | Per-shot status from 11C + per-node timings from 11B | <work-dir>/node11_result.json + stdout summary line | Python json + datetime | Locked decisions #11 (single consumable JSON artifact) + #12 (consistent CLI summary shape with other 9 nodes). NO active VRAM monitoring (#8) -- documented as known limitation.
| 11E | Exit-code resolution | Exit 0 if at least one shot succeeded (partial success counts as 0); exit 1 if all failed (BatchAllFailedError) or on Node11Error subclass (InputDirError, NodeStepError); exit 2 on unexpected exception. | Per-shot status from 11C | Process exit code 0 / 1 / 2 | Python sys.exit | Locked decision #13 (Node 11 owns the partial-success semantic; individual nodes can't because they fail the whole batch by design). Differs from Nodes 2-10's exit-code policy intentionally.
| 7v2-A | Phase 2a — Flux + Style LoRA + Union CN integration | Replace Phase 1's SD 1.5 + AnyLoRA workflow with a Flux Dev fp16 + Flat Cartoon Style v1.2 LoRA + ControlNet Union Pro stack. txt2img mode for first ship (img2img comes in Phase 2c). Add precision-fallback for smaller GPUs. Default still v1 for safety; v2 callable via --workflow flag. | Existing Phase 1 inputs (node6_result.json + queue.json) + new Flux + LoRA + Union CN weights downloaded by runpod_setup.sh per models.json pins. | New custom_nodes/node_07_pose_refiner/workflow_flux_v2.json (16 locked node IDs); modified models.json (Phase 2 weights added; Phase 1 weights flipped to deprecated:true with scheduled removal 2026-10-26); modified runpod_setup.sh (Phase 2 weight downloads + DOWNLOAD_DEPRECATED env var handling); modified pipeline/cli_node7.py (new --workflow {v1,v2} default v1 + --precision {fp16,fp8} default fp16 flags); modified custom_nodes/node_07_pose_refiner/orchestrate.py (routing + Flux variable substitution); test_node7.py Phase 2 cases. | Flux Dev fp16/fp8 (BFL); T5-XXL fp16/fp8; CLIP-L; Flux VAE (ae.safetensors); Flat Cartoon Style v1.2 (Civitai 644541 v 740091); ControlNet Union Pro (Shakker-Labs); ai-toolkit not yet (Phase 2d). | Hug-test proof-of-concept at _pod_out/flux_tmkoc_test_workflow.json is the implementation starting point for workflow_flux_v2.json. Per-node ship checklist applies (CLAUDE.md ship checklist section). Phase 2 schema additions (per #10 backward-compat): models.json gains deprecated/deprecatedSince/deprecatedReason/scheduledRemovalDate/precision fields (all optional with defaults). RefinedGeneration manifest gains workflowName/precision/characterLoraFilename fields (optional, default 'v1'/'fp8'/None for Phase 1 round-trip). CLI flags pass through Node 11 unchanged. Status (2026-04-26): SHIPPED — same day as design-lock, mirroring the Nodes 8-11 pattern (design-lock + ship same day). 84 Node 7 tests pass (47 Phase 1 + 37 new Phase 2; 429 repo-wide, zero regressions on every prior Node 2-11 test). Files shipped: custom_nodes/node_07_pose_refiner/workflow_flux_v2.json (16 locked Phase 2 node IDs); modified custom_nodes/node_07_pose_refiner/{orchestrate.py, manifest.py, models.json, __init__.py, README.md} + pipeline/{cli_node7.py, cli_node11.py, node11.py, node2.py, schemas.py} + runpod_setup.sh + tests/{test_node7.py, test_node11.py, test_node2.py}. Default --workflow=v1 means existing pipelines keep working unchanged; v2 is opt-in via the new flag until Phase 2c lands. Phase 1 weights flipped to deprecated:true with 2026-10-26 removal date; runpod_setup.sh skips them by default (DOWNLOAD_DEPRECATED=true opts back in for rollback). Phase 2b is the next ship-checklist step — XLabs Flux IP-Adapter v2 via x-flux-comfyui custom node clone.
| 7v2-B | Phase 2b — Add XLabs Flux IP-Adapter | Add identity-injection layer to Phase 2a's workflow via the XLabs-AI Flux IP-Adapter v2 (~1 GB weight). Wires character reference crop into the Flux stack so generated character matches the model sheet across multiple key poses. Reuses Node 6's color reference crops (no Node 6 changes here). | Phase 2a workflow + Node 6's color reference crops (existing). | Modified runpod_setup.sh (clones x-flux-comfyui custom node from XLabs-AI; downloads flux-ip-adapter-v2.safetensors); modified workflow_flux_v2.json (IP-Adapter nodes wired in); identity-preservation regression test on the TMKOC fixture (same character across multiple key poses must have consistent face / outfit). | XLabs-AI x-flux-comfyui custom node; flux-ip-adapter-v2.safetensors weight; T5-XXL + CLIP-L (already loaded by Phase 2a's DualCLIPLoader). | IP-Adapter strength 0.8 default per locked decision #6. Phase 2b's IP-Adapter alone may produce ~85% identity quality, sufficient for many shots without the full per-character LoRA stack from Phase 2e (which pushes to ~95%). Status (2026-04-27): SHIPPED. 91 Node 7 tests pass (47 Phase 1 + 44 Phase 2; 436 repo-wide, zero regressions). Wired XLabs Flux IP-Adapter v2 into workflow_flux_v2.json via 3 additive locked node IDs: 22 ('Load Flux IPAdatpter' [sic - upstream typo preserved verbatim because that's the registered class_type], 23 (LoadImage for the reference COLOR crop from Node 6E), 24 ('Apply Flux IPAdapter'). Only existing-node change is KSampler's model input rewiring from node 20 (style LoRA output) to node 24 (IP-Adapter wrapped model). ip_scale=0.8 per locked decision #6 (XLabs default is 0.93; we trade a bit of identity strength for slightly looser pose adherence -- better for varied keyposes across a shot). Reference image is the COLOR crop, NOT the DoG line-art crop, per locked decision #4. models.json gained 2 new weight pins: flux-ip-adapter-v2.safetensors (~1 GB at models/ipadapter-flux/) and clip-vit-large-patch14.safetensors (~600 MB at models/clip_vision/ for the IP-Adapter's vision encoder; distinct from the Phase 2a clip_l text encoder). models.json customNodes also gained the x-flux-comfyui clone from XLabs-AI. orchestrate.py gained NODE_FLUX_IPADAPTER_LOADER/_REF_IMAGE/_APPLY constants + parameterizer wires task.referenceColorCropPath into node 23 + re-asserts ip_scale = V2_STRENGTH_IP_ADAPTER. 7 new tests cover the shipped-JSON regression (IP-Adapter nodes present + correct class_type strings with typos + KSampler rewired to node 24 + IP-Adapter Apply inputs wired correctly), parameterizer behaviour (reference color -> node 23, ip_scale -> V2_STRENGTH_IP_ADAPTER, rough-vs-reference path-swap guard), and fail-loud regression (missing IP-Adapter node raises WorkflowTemplateError). Phase 2c is the next ship-checklist step -- switch workflow_flux_v2.json from txt2img to img2img + flip --workflow default from v1 to v2. Phase 2d-fixup (2026-04-27, post-live-pod-debug): Live-pod verification on a fresh A100 80GB caught two real bugs in Phase 2b's ship that would have blocked Phase 2d-run / Phase 2e-run when actually invoking ComfyUI's HTTP API. (1) workflow_flux_v2.json had class_type 'Load Flux IPAdatpter' and 'Apply Flux IPAdapter' on nodes 22 + 24. ComfyUI's /object_info reported those classes NOT registered — but 'LoadFluxIPAdapter' and 'ApplyFluxIPAdapter' (no spaces, no typo) WERE registered. Phase 2b's agent research confused upstream's NODE_CLASS_MAPPINGS keys (the internal class names ComfyUI's wire format uses) with NODE_DISPLAY_NAME_MAPPINGS values (the GUI menu labels, where the 'IPAdatpter' typo lives). Workflow JSON's class_type field uses the keys, not the values. (2) models.json IP-Adapter destination 'models/ipadapter-flux/' was wrong — x-flux-comfyui's folder_paths.folder_names_and_paths['xlabs_ipadapters'] registration scans 'models/xlabs/ipadapters/' (os.path.join(models_dir, 'xlabs', 'ipadapters')). Files in the wrong dir never appear in LoadFluxIPAdapter's ipadatper field. Phase 2d-fixup corrects: workflow_flux_v2.json class_type strings + file-level _comment; models.json destination + both role descriptions; orchestrate.py NODE_FLUX_IPADAPTER_LOADER comment + _require_node human-name strings; tests/test_node7.py pinned strings (test_shipped_workflow_flux_v2_ipadapter_class_types) + _minimal_v2_template placeholder + test_v2_parameterize_missing_ipadapter_node_raises regex match; custom_nodes/node_07_pose_refiner/README.md Phase 2b row + 17-row workflow node ID table + footer note explaining wire-protocol class_type vs GUI display name distinction. The 'ipadatper' input FIELD name (typo'd) IS real and stays as-is — that's how XLabs registered the field name in LoadFluxIPAdapter.INPUT_TYPES. 449 tests pass after the fix; zero regressions. Pod was terminated to save budget; Phase 2d-run (actual TMKOC LoRA training) resumes on a fresh pod when the user has rendered episode shots downloaded. Phase 2-revision (2026-04-28, post-design-review): Real-shot test on the Phase 2c v2 stack produced colored TMKOC scenes (via colored prompts) on whole-frame img2img output. Two design regressions caught at the same time: (1) Phase 2c implemented 'img2img on the rough crop' as VAEEncode of the WHOLE-FRAME keypose at node 50, breaking Phase 1 locked decision #5 (per-character generation, NOT whole-frame inpaint) — BG furniture and other characters got pulled into Flux's view. (2) Phase 2c prompts asked for 'flat cartoon style ... bright daytime colors' and rejected 'monochrome', biasing v2 toward color — but Part 1's locked spec is BnW line art on white. Phase 2-revision corrects three things at once: (1) `_run_one_task` pre-crops keypose to (Node-5 bbox + 20% margin) via new `_prepare_rough_bbox_crop` helper, clamped to image bounds + resized to multiples of 16 (Flux requirement) with longest edge ≤ 768; the bbox crop becomes node 50's input so pose preprocessor + VAEEncode + KSampler all operate on character-only pixels. The parameterizer accepts a new `rough_image_override` parameter so production runs pass the bbox-crop path while parameterizer-only unit tests fall back to `task.keyPosePath`. (2) `V2_POSITIVE_PROMPT_TEMPLATE` swapped from 'flat cartoon style ... bright daytime colors' → 'clean black ink line art ... white background, no fill, no color'. `V2_NEGATIVE_PROMPT` swapped from rejecting 'monochrome' → rejecting 'color, fill, shading, scene, furniture'. The negative no longer rejects 'monochrome' (Phase 2c's bug — that was rejecting exactly what Part 1 wants). (3) New `STYLE_LORA_STRENGTHS` per-LoRA strength table — `flat_cartoon_v12 → 0.0` (LoRA loads but is bypassed because it biases toward color, conflicting with Part 1's BnW deliverable; LoraLoader can't be skipped without rewiring nodes 30 + 24), `tmkoc_v1 → 0.75` (locked decision #2 production value, applied automatically once Phase 2d-run ships the custom-trained LINE-ART LoRA). Locked decision #2 ("style LoRA at 0.75") survives intact for the LoRA we actually want to use. `workflow_flux_v2.json` node 20 strength updated to 0.0 in JSON; `V2_STYLE_LORA_STRENGTH` constant retained for backwards compat. Phase 2d training-data approach also flipped: PHASE2D_TRAINING_PLAYBOOK.md revised end-to-end from synthetic Path A bootstrap → user's storyboard scene cuts directly (clean BnW digital lines on white BG; already in the target aesthetic; per-iteration cost drops from ~$10-15 + 12-18 hrs to ~$3-5 + 4-8 hrs). 9 new tests + 2 modified tests cover the per-LoRA strength table + BnW prompt assertions + bbox-crop helper + rough_image_override mechanism + regression guards on the shipped JSON's node 20 strength=0.0. Net effect: v2's deliverable now matches Phase 1's deliverable shape (per-character BnW line-art PNGs Node 8 composites onto a white-BG frame at bbox positions), but with Flux's superior generation quality + character identity preservation via XLabs IP-Adapter. The 14 original Phase 2 locked decisions stand; Phase 2-revision corrects the implementation regression that contradicted decisions #4 + #5 and Part 1's BnW deliverable. Phase 2-revision-fixup-1 + -fixup-2 (2026-04-28, post-live-pod-debug): live smoke on a fresh A100 80GB caught two bugs the dry-run + parameterizer-only unit tests missed because they only manifest on the live _run_one_task non-dry-run path that contacts ComfyUI's HTTP API. (1) orchestrate.py's Phase 2-revision bbox-crop block calls _safe_segment(task.identity) to build the per-detection crop filename; _safe_segment lives in manifest.py and orchestrate.py never imported it. Every Node 7 detection died with NameError before any ComfyUI POST. Fix: added _safe_segment to orchestrate.py's `from .manifest import (...)` block + new regression test test_orchestrate_imports_safe_segment_from_manifest. (2) workflow_flux_v2.json node 22 LoadFluxIPAdapter had `provider: "CUDA"` but x-flux-comfyui's INPUT_TYPES registers provider as ["CPU", "GPU"]; ComfyUI's prompt validator rejected every workflow with "Value not in list: provider: 'CUDA' not in ['CPU', 'GPU']". Phase 2b's agent-research used the underlying CUDA provider name instead of the dropdown value. Fix: changed to "GPU" + new regression test test_shipped_workflow_flux_v2_ipadapter_provider_is_valid. Live-pod smoke verified end-to-end through Node 7's ComfyUI submission step before the bug fired (Nodes 2-6 ran cleanly: 88 frames decoded → 3 keyposes → 6 detections → 6 reference matches; Phase 2f's <shot>/dark_lines/ generated 3 BnW PNGs as expected). 116 Node-7 tests pass after both fixups (114 pre-fixup + 2 new regression tests). 3rd smoke retry to visually verify per-character BnW output was BLOCKED 2026-04-28 by RunPod credit exhaustion; resume with credit recharge.
| 7v2-C | Phase 2c — Switch Node 7 default to v2 (img2img mode, denoise=0.55) | Flip --workflow default from v1 to v2; switch workflow_flux_v2.json from txt2img to img2img mode. Rough crop is VAEEncoded into the latent and KSampler runs at denoise=0.55 — preserves rough composition (positions, scale, silhouette) while regenerating line quality + character identity. Phase 1 path stays callable via --workflow=v1 throughout the 6-month deprecation window. | Phase 2b workflow + Node 5/6/7 inputs unchanged. | Modified workflow_flux_v2.json (LoadImage node 50 + VAEEncode node 80 wired in place of EmptySD3LatentImage; KSampler node 90's denoise param set to 0.55); modified pipeline/cli_node7.py (--workflow default flips to v2); end-to-end real-shot validation against TMKOC fixture (5+ shots). | Same as Phase 2b stack; no new weights or custom nodes. | Locked decision #5 reverses Phase 1's txt2img — Flux Kontext Dev's superior denoising resolves the original 'rough pixels would bleed into output' concern. denoise=0.55 is the locked default; tuning per-shot is a future operator concern. After Phase 2c lands, Phase 2 is the production path; v1 stays as rollback insurance only. Status (2026-04-27): SHIPPED. 96 Node 7 tests pass (47 Phase 1 + 49 Phase 2; 441 repo-wide, zero regressions). TWO architecturally significant flips: (1) workflow_flux_v2.json node 80 swapped from EmptySD3LatentImage(1280, 720) [txt2img] to VAEEncode(pixels=node-50, vae=node-12) [img2img] -- the rough crop now feeds into the latent via Flux's VAE; KSampler denoise dropped from 1.0 to 0.55 per locked decision #5. Flux Kontext Dev's superior denoising resolves Phase 1's 'rough pixels would bleed into output' concern -- at 0.55 the messy pencil scribbles vanish but the underlying composition (positions, scale, silhouette) stays. Output dimensions match the rough's native dims (Node 4 wrote them at source MP4 resolution); Node 8's compositor places refined PNGs at bbox positions per Node 8's locked decision #1, so exact output dims don't matter. (2) DEFAULT_WORKFLOW flipped from 'v1' to 'v2' in orchestrate.py -- v2 is now the production default; Phase 1 stays callable via --workflow=v1 for the entire 6-month deprecation window per locked decision #12 (until 2026-10-26). V2_DENOISE = 0.55 constant added; v2 parameterizer re-asserts it on every generation so a hand-edited JSON can't silently revert to txt2img's denoise=1.0. CLI success line for v2 reports 'precision=<value>' alongside 'workflow=v2' (was hidden under v1). 5 new tests cover img2img wiring (node 80 = VAEEncode with pixels from 50 + vae from 12 in shipped JSON), denoise lock (KSampler.denoise = 0.55 in shipped JSON + parameterizer re-asserts it), v2-as-default (DEFAULT_WORKFLOW + cfg.workflow + CLI success line all expect v2), and v1-still-callable-via-flag. 3 existing tests updated to pass workflow='v1' explicitly where they meant Phase 1 specifically (test_cn_strengths_for_dwpose, test_cn_strengths_for_lineart_fallback, test_cn_strengths_for_v1_explicit_returns_v1_split). Phase 2d is the next ship-checklist step -- replace generic Flat Cartoon Style v1.2 with a custom-trained TMKOC v1 style LoRA bootstrapped from Phase 2c's img2img output.
| 7v2-D | Phase 2d — Train TMKOC style LoRA | Replace generic Flat Cartoon Style v1.2 with a custom-trained TMKOC v1 style LoRA. Higher per-shot fidelity to the actual Indian children's animation aesthetic (vs. generic flat-cartoon). Optional but recommended for client-deliverable quality. | Training data: curated TMKOC frame extracts OR Phase 2c img2img output from prior client batches OR commissioned artist references. ~50-100 high-quality training images. | Trained LoRA weight tmkoc_style_v1.safetensors; modified models.json (new LoRA pinned with sha256); modified workflow_flux_v2.json (LoraLoader node 20's lora_name swapped from flat_cartoon_style_v12 to tmkoc_style_v1). | ai-toolkit (ostris) on A100 80GB; ~1.5h training + ~$5 RunPod time. CogVLM or GPT-4V for image captioning before training. | Caption discipline matters: caption everything that ISN'T the TMKOC style (subject, pose, expression, background) so the LoRA learns 'TMKOC style' as the residual rather than memorizing specific scenes. Strength tuning per-LoRA (start at 0.75, adjust 0.6-0.9 based on test runs). Status (2026-04-27): Phase 2d-prep SHIPPED; Phase 2d-run pending. 104 Node 7 tests pass (47 Phase 1 + 57 Phase 2; 449 repo-wide, zero regressions). Shipped the integration infrastructure for the TMKOC v1 style LoRA without yet training the actual safetensors weight (Phase 2d-run is a separate live-pod follow-up). Code: new --style-lora {flat_cartoon_v12,tmkoc_v1} flag (default flat_cartoon_v12) on pipeline/cli_node7.py + pipeline/cli_node11.py + ComfyUI wrapper style_lora dropdown -- parameterizes workflow_flux_v2.json node 20's lora_name based on the choice. STYLE_LORA_FILENAMES table + STYLE_LORA_CHOICES + DEFAULT_STYLE_LORA constants in orchestrate.py; OrchestrateConfig.__post_init__ validates the field. tmkoc-style-v1 placeholder entry added to models.json with url='TODO...' so runpod_setup.sh skips it gracefully until a real weight URL+sha256 ships -- destination models/loras/tmkoc_style_v1.safetensors, sizeMB ~80, role describes the contract. New files: tools/phase2d/PHASE2D_TRAINING_PLAYBOOK.md (full Path A bootstrap -> curate -> caption -> train -> validate -> ship runbook; 6-step procedure with cost/time estimates: ~$10-15 GPU + ~12-18 hours human time per LoRA across 2-3 iterations) and tools/phase2d/ai_toolkit_config_template.yaml (locked Flux LoRA training params: rank=16, LR=1e-4, 2000 steps, batch_size=1, quantize=true, sample_every=250 -- operator copies it to a per-run name and fills 3 TODO fields before launching ai-toolkit). 8 new tests cover the flag plumbing (CLI accepts/rejects + default flat_cartoon_v12 + tmkoc_v1 swap), parameterizer wiring (node 20 lora_name flips per choice), config validation (invalid choice raises ValueError), and the contract between STYLE_LORA_FILENAMES and models.json destinations. Phase 2d-run is the next ship-checklist step -- actually train the TMKOC v1 LoRA on a live A100 pod by following the playbook, then a follow-up commit fills in models.json's tmkoc-style-v1 URL + sha256 from the trained safetensors weight.
| 7v2-E | Phase 2e — Train per-character LoRAs (one commit per character) | Optional max-quality identity injection: stack a character-specific LoRA (e.g. TAPPU_v1.safetensors, CHAMPAK_LAL_v1.safetensors) on top of the TMKOC style LoRA. Pushes identity quality from ~85% (IP-Adapter alone) to ~95%. Per-character LoRAs are loaded via a chained LoraLoader (node 21) selected per-detection from characters.json.characterLoraFilename. | Per character: 50-100 training images bootstrapped from the model sheet via Phase 2b's IP-Adapter (generate variations, curate best 60-80, caption with CogVLM/GPT-4V). | Per character: trained <NAME>_v1.safetensors; modified models.json (new LoRA pinned); modified characters.json (characterLoraFilename + characterLoraStrength fields populated for the character — additive schema per #10 means old characters.json files still load with these fields null/0.85). Per-character ComfyUI test (10+ generations across varied poses) verifies consistent identity. | Same ai-toolkit + A100 80GB stack as Phase 2d; ~1.5h + ~$5-15 per character. | Order matters per Phase 2 locked decision #9: train per-character LoRAs ONLY after Phase 2d's TMKOC style LoRA ships — character LoRAs trained against the wrong base style would need re-training when style changes. Strength stacking: style LoRA at 0.75 + character LoRA at 0.85 (tune per character; over-stacking causes the two LoRAs to fight). One ship-checklist commit per character, mirroring per-node discipline.
| 7v2-F | Phase 2f - Fix Node 5 background-line detection bug (DONE 2026-04-28) | Real TMKOC test exposed a Node 5 failure mode: when the rough animatic has sketched BG lines, Otsu binarization treated all dark-vs-light pixels as one foreground class, swallowing the actual characters or falsely tagging the BG as a giant single character. The user identified the real semantic signal: character outlines are dark bold black (~0-50 luminance) while BG furniture is light grey (~80-180). Phase 2f replaces Otsu with a fixed luminance threshold + 3x3 morphological closing. | Existing Node 5 inputs (node4_result.json + queue.json). | Modified pipeline/node5.py: new _extract_dark_lines + _close_outline_gaps + _save_dark_lines_png + _wipe_dark_lines_dir helpers; --dark-threshold N CLI flag; <shot>/dark_lines/<filename>.png side-effect (BnW: black ink on white BG) per keypose. Modified custom_nodes/node_07_pose_refiner/orchestrate.py: new _resolve_dark_lines_source resolver that _prepare_rough_bbox_crop calls before reading the source PNG. | scipy.ndimage.binary_closing (existing Node 5 dep); Pillow (existing Node 5 dep); no new packages. | Out of strict Node 7 scope but blocking real Phase 2c quality verification. Schedule: ship before or alongside Phase 2c so Phase 2c's first real client validation isn't sabotaged by Node 5 garbage upstream. DONE 2026-04-28. Original sketch ('Otsu fallback when bbox > 70% of frame + ROI hint via metadata') was a heuristic-based size check; the user's 'dark vs light line' insight is a much better semantic signal that's actually in the artwork. 70 Node 5 tests pass (+20 new) + 114 Node 7 tests pass (+4 new); 479 repo-wide, zero regressions. Schema additions additive (CharacterMap gains darkThreshold + darkLinesDir; Node5Result gains darkThreshold; schemaVersion stays at 1) so old work dirs load unchanged. Backward-compat fallback: when <shot>/dark_lines/ is missing (pre-Phase-2f work dirs), Node 7 reads from the raw keypose, no migration step required.
| 7v2-G | Phase 2g - Simplify Node 6 (always pick 'front' angle when IP-Adapter handles identity) (DONE 2026-05-03) | Default angle_mode = 'front-only'. The original 2026-04-23 multi-signal silhouette scoring is RETAINED as opt-in via --angle-mode auto. Reason: IP-Adapter needs the character's FACE for identity learning; back-view crops give it nothing useful. Live-pod test 2026-05-03 caught Node 6's 'auto' picking back-3q-R for a front-facing rough -> IP-Adapter saw the back of TAPPU's head -> output was generic bald-old-man. Front-view always shows the character's face. | Existing Node 6 inputs (node5_result.json + queue.json + characters.json). | Modified pipeline/node6.py: new ANGLE_MODES + DEFAULT_ANGLE_MODE + FORCED_FRONT_ANGLE constants; angle_mode parameter threaded through match_references_for_queue + match_references_for_shot + _match_one_detection; override loop after silhouette scoring; phase2g_override marker in scoreBreakdown. CLI: pipeline/cli_node6.py + custom_nodes/node_06_reference_matcher gained --angle-mode flag. Schema: Node6Result gains angleMode: str. | scipy + Pillow (existing Node 6 deps); no new packages. | Optional simplification — Node 6's classical multi-signal angle picker still works and can stay the default. front-only mode is a Phase 2b+ optimization since the IP-Adapter does the identity heavy-lifting from a single reference angle just as well as from the 'best' angle. DONE 2026-05-03. 9 new tests + 1 modified angle test; 43 total Node 6; 500 repo-wide, zero regressions. Schema additive (schemaVersion stays at 1) so old node6_result.json files load unchanged.
| 7v2-Tune | Phase 2f-tuning - Adaptive iterative dilation before CC for character outline gaps (DONE 2026-05-03) | Phase 2f's 3x3 morphological closing only seals 1-2 pixel gaps in character outlines. Storyboard art commonly has 5-15 pixel gaps where the artist lifted the pen between strokes (head outline doesn't touch torso outline, etc.). Character fragments into 4-6 CCs and Node 5's reconcile drops the wrong fragments. Live-pod test 2026-05-03 caught Node 5 detecting bbox=178 px tall when the actual character was ~430 px tall. Adaptive iteration count handles all camera framings (wide shots / medium / close-ups) automatically since metadata's expected_count is the target. | Same Node 5 inputs (node4_result.json + queue.json) + new --bbox-max-dilation N flag (default 15). | Modified pipeline/node5.py: new _detect_bboxes_adaptive function; bbox_max_dilation parameter threaded through detect_characters_for_queue + detect_characters_for_shot + _detect_on_key_pose. Schema: CharacterMap + Node5Result gain bboxMaxDilation field. New CLI/ComfyUI flag exposes the cap. New bbox-adaptive-dilation warning records the chosen level per-keypose. | scipy + numpy (existing Node 5 deps); no new packages. | DONE 2026-05-03. 7 new tests; 77 total Node 5; 500 repo-wide, zero regressions. Adaptive algorithm: try dilation in [0, 1, 2, 3, 5, 7, 10, max_dilation], pick the level whose significant-blob count is closest to expected_count (preferring fewer dilations on ties to reduce risk of over-merging adjacent characters). Schema additive (schemaVersion stays at 1).
| 7v2-FixUp3 | Phase 2-revision-fixup-3 - runpod_setup.sh x-flux-comfyui auto-patch + Node 11 timeout passthrough + PyTorch cu13 docs (DONE 2026-05-03) | Live-pod-debug bundle for issues that bit between Phase 2-revision and the user's 3rd live-pod smoke. (a) Recent ComfyUI core (>= 0.19) calls Flux blocks with attn_mask=... kwarg but x-flux-comfyui's signatures don't declare it -> TypeError on every prompt. (b) Node 11's default 600s per-prompt timeout is too short for slow Flux (CPU fallback or complex shots) -> orchestrator marks every detection as error even though ComfyUI is still generating in the background. (c) PyTorch 2.4.x + cu13 driver = Flux loads to GPU memory but actual sampling falls back to CPU at 12+ min/generation. | Modifies runpod_setup.sh, pipeline/cli_node11.py, pipeline/node11.py, tools/POD_NOTES_runpod_slim.md. | (a) runpod_setup.sh now sed-patches **kwargs into x-flux-comfyui's DoubleStreamBlock + SingleStreamBlock forward signatures right after git clone (idempotent). (b) Node 11 CLI gained --per-prompt-timeout SECONDS flag that passes through to Node 7 via _build_argv_for_node. (c) runpod_setup.sh warns at startup if PyTorch < 2.5 detected. tools/POD_NOTES_runpod_slim.md gains a Phase 2-revision-fixup-3 section documenting all four issues (this + the missing-files git-checkout issue + the x-flux-comfyui patch + the timeout passthrough). | bash + sed (runpod_setup.sh); argparse (CLI); no new Python packages. | DONE 2026-05-03. 3 new Node 11 tests for timeout passthrough; 49 total Node 11; 500 repo-wide, zero regressions. The PyTorch upgrade itself is NOT done by runpod_setup.sh (the operator must `pip install --upgrade 'torch>=2.5,<2.7' --index-url https://download.pytorch.org/whl/cu130` manually); the warning + docs are the actionable signal.

## Legend
Field | Meaning
Node | Top-level stage of the pipeline (1-11).
Sub-step | Granular action inside a node (e.g. 1A, 1B).
Name | Short name of the sub-step.
Purpose | Why this sub-step exists.
Inputs | What this sub-step consumes.
Outputs | What this sub-step produces.
Tools / Tech | Recommended technology / library.
Notes | Design decisions, constraints, open questions.
Position code | Meaning
L | Left
CL | Center-Left
C | Exact Center
CR | Center-Right
R | Right
Frame rate | 25 FPS (fixed)
Output color | Black & White Line Art
Scope | Part 1 only - ToonCrafter in-betweens handled in Part 2